## AI Governance
AI Governance
Scope |  |  | 1. Deliver the AI Governance research and benchmarking across providers covering Integration requirements, and comparison of all key metrics and features, but not limited to, - Cost: Token pricing tiers (GPT-4 vs. Claude Sonnet vs. Gemini ), agent session costs, provisioned throughput discounts - Agentic Capabilities: Tool-calling quality (OpenAI Functions vs. Bedrock Custom Tools vs. Vertex Function Calling), reasoning chains (o1-preview vs. Claude Opus), multi-agent orchestration - Guardrails: Native filters (Bedrock Guardrails vs. Vertex Content Safety vs. OpenAI Moderation API), PII detection accuracy, custom policy support - Performance: Latency (ms/query), context window (1M+ tokens), RAG integration ease across enterprise tasks 2. API Integration: API integration with provider APIs to discover AI models, collect usage, cost, and performance data, and normalize governance datasets for cross-cloud visibility. 3. AI Governance FinOps Visibility: - Develop a centralized dashboard that aggregates token usage, input/output metrics, and costs per user, model, and provider. - Implement granular reporting with breakdowns and anomaly detection for multi-provider spend. - Deliver AI Agents that analyze usage patterns across providers to enable predictive cost forecasting. 4. AI Governance Optimization & Automation: Create automated workflows for model routing, caching, and prompt optimization across providers. 5. Pre-Deployment Terraform Guardrail Scanning in Azure DevOps : Generate AI-driven guardrails for all providers and integrate with the CI/CD pipeline.
Phase | Week | Phase Type | Focus Area | Description | Technical Output / Deliverables | CS Dependencies
Phase 1 | 1 | API Analysis | Multi-Provider AI APIs And Governance Foundations | Understand AWS Bedrock, GCP Vertex AI, and OpenAI APIs, IAM roles, service accounts, and integration requirements. Review AI governance, benchmarking dimensions, and FinOps concepts. Set up Python automation environment. AWS Bedrock : https://docs.aws.amazon.com/bedrock/latest/APIReference/welcome.html?utm_source=chatgpt.com GCP Vertex AI : https://docs.cloud.google.com/vertex-ai/docs Open AI : https://platform.openai.com/docs/api-reference/authentication | Python environment setup, validated API access. | GCP account access (Velan will provide the document for new account creation) ETA: 20th Jan
Phase 1 | 2,3,4 | AI Governance Research & Benchmarking | AI Governance Data Models And Benchmarking Metrics | Deliver the AI Governance research and benchmarking across providers covering Integration requirements, and comparison of all key metrics and features, but not limited to, - Cost: Token pricing tiers (GPT-4 vs. Claude Sonnet vs. Gemini ), agent session costs, provisioned throughput discounts - Agentic Capabilities: Tool-calling quality (OpenAI Functions vs. Bedrock Custom Tools vs. Vertex Function Calling), reasoning chains (o1-preview vs. Claude Opus), multi-agent orchestration - Guardrails: Native filters (Bedrock Guardrails vs. Vertex Content Safety vs. OpenAI Moderation API), PII detection accuracy, custom policy support - Performance: Latency (ms/query), context window (1M+ tokens), RAG integration ease across enterprise tasks | AI Governance Requirements document | NA
Phase 1 | 5,6,7,8 | AI Governance Architecture & Solutioning | API Integration And FinOps Visibility, Optimization And Automation Solution | Architecture & Solutioning for 1. API Integration: API integration with provider APIs to discover AI models, collect usage, cost, and performance data, and normalize governance datasets for cross-cloud visibility. 2. AI Governance FinOps Visibility: - Develop a centralized dashboard that aggregates token usage, input/output metrics, and costs per user, model, and provider. - Implement granular reporting with breakdowns and anomaly detection for multi-provider spend. - Deliver AI Agents that analyze usage patterns across providers to enable predictive cost forecasting. 3. AI Governance Optimization & Automation: Create automated workflows for model routing, caching, and prompt optimization across providers. 4. Pre-Deployment Terraform Guardrail Scanning in Azure DevOps : Generate AI-driven guardrails for all providers and integrate with the CI/CD pipeline. | Architecture Solution Implementation Document | NA
Phase 2 | 9,10,11,12 | AI Governance Implementation | AI Governance Execution | Solution Implementation: - Vertex AI, AWS Bedrock, and OpenAI API integration for model discovery and usage metrics collection - Normalization of cross-provider datasets into a unified governance schema using Python, Ingest raw API data, map provider-specific metrics to standardized fields, implement NoSQL schema for cost, performance, agentic, and guardrail metrics, and store in a central data repository - Build the FinOps dashboards with token usage, cost tracking, anomaly detection, and predictive forecasting using BI tools - Build AI Agent for usage patterns across providers to enable predictive cost forecasting - Implement automated workflows for cross-provider model routing, response caching, and prompt optimization based on cost, performance, and governance policies - Implement automated pre-deployment scanning of Terraform templates in Azure DevOps pipelines to validate AI governance guardrails and generate compliance and violation reports | Governance solution including API automation, normalized datasets, dashboards, AI agent, and Terraform-based guardrails. | Reference Azure OpenAI automation script
Phase 2 | 13, 14 | Project Documentaion & Review | Final Review, Documentation And Handover | Review/Document and consolidate all work, including research, architecture, implementation, dashboards, and guardrails. | Final documentation, dashboards, Governance policies and pre-deployment scanning of Terraform templates in Azure DevOps | NA